Crater CEDS Meeting Minutes

9/25/23

12:00pm – 2:00pm

Attendees:

Andrew Franzyshen- Crater PDC

Hannah Woehrle- Crater PDC

Kit Friedman- Crater PDC

Wendy Austin- Friends of the Lower Appomattox River

Loren Sodell- VSU/ CCAMS

Liz Povar- River Link Group

Morgan Ingram- Dinwiddie County

Ann Isbell- GOVA Region 4

Horace Wade- Surry County

Natalie Slate- Greensville County

Becky McDonough- Hopewell/Prince George Chamber of Commerce

Elizabeth Creamer- Community College Workforce Alliance

Heather Lyne- Hopewell Downtown Partnership

Devon Keeler- Dewberry

Yoti Jabri- Prince George County

Lynne Mann- Crater APEX Accelerator

12:00 – Settle-in, get lunch, get acquainted

12:15 – Recap of last meeting

12:30 – Sub-committee updates/review goals

Infrastructure

- Regional broadband

- Water/Sewer Plan

- Electric/Utilities Database

  - Accounting for capacity and type of electric supplied to economic development sites to share with prospective developers

- Transportation Project Advocacy

Small Business

- Revolving Loan Funds

- Support REI

- Bolster Referrals and visibility for partner programs

- Small business approach to workforce development

  - Small businesses are too busy to take advantage of SBA resources

  - Convene small business owners and ask directly—focus groups

    - Incorporate APEX and Chambers of Commerce

    - What types of training is missing and how should it be delivered

  - Amplifying existing resources and connecting business owners

    - Visibility—website landing page, one-pager, clearinghouse/concierge

    - Minimizing paperwork and manpower hours to connect to resources

- Grant writing assistance

Quality of Life

- Regional housing study

- Agribusiness/agritourism study

  - GOVA could get involved in funding with a planning grant

    - Agri technology

  - VDACS funding, APHIS/USDA funding

- Completion of FLT and ART

- Engaging all localities in PART

- Community/Regional branding—amplify existing local efforts

  - Rehabbing regional image

  - Proximity to Richmond—affordability

  - Branding/Marketing Study

    - Pulling information from locality comprehensive plans—close readings

    - Trends

Workforce Development

- Regional strategic plan (WFDB)

- Targeted Outreach Plan

  - “telling the story”

  - Communications workshops

- Central repository

  - State website for workforce development resources to be linked/housed/searched

  - Advertise to account for high turnover across industry and local government

- Convene CTE Program reps

- Info sheet for employers

- Higher education/research action items included in Workforce Development

  - Need to better promote services to industries and potential employers

  - Need a centralized location to provide info on employee training during industry visits

  - Advertising to employers to help build pipeline

    - Training program already exists at Brightpoint—how to advertise and engage people

- Defining who falls under “Workforce”

- GOVA Resources are counterproductive to regional needs

  - Trades and gaps in trade industries

- Retention of the 24-year-old population

  - Pull data on youth workforce data

- Regional Technical School

  - PDC as a convening arm--consortium

    - Design/Deploy/Deliver technical training to targeted sectors

    - Involving employmers

  - Singular school for entire Crater region isn’t possible due to geographic spread

  - Vacant space in Hopewell with talks of being converted into technical school?

    - Does it need to be an action item in this CEDS?

  - Used to be night classes—can we get them back? Partnerships

  - Dinwiddie school, Greensville County bringing back Dual Enrollment

- GOVA programs

Targeted Industry Sectors

- Regional water/sewer plan

- Electric Database

- Multimodal Plan

1:00 – Discuss Implementation and Performance Measurement

Timeline/Performance Measures

- Regional Broadband Report

  - 12-18 months to compile information in a usable way

    - BEAD/VATI funding is rolling out

- Regional Water/Sewer Plan

  - Dependent upon each locality/expectations/funding

  - 24-36 months

  - State and federal funding availability

- Electric Database

  - Tighter timeline

  - Phased:

    - Phase 1: 12-18mo updated annually

- Transportation Project Advocacy

  - Ongoing

- Performance Measures:

  - Coverage metrics (%)—establishing regional short-term targets versus general increase/decrease

    - Planned areas for water/sewer, economic development sites

    - Will differ based on locality

    - Discrepancies between FCC map coverage and actual access, adoption, etc.

  - Reports will help up identify targets

______________________________________________________________________________

- Reestablish Revolving Loan Fund

  - Microloan

  - ~12-24mo

- Support REI

  - End of 2023

- Bolster Visibility for Partner Programs

  - ongoing

- Small Business Approach to Workforce Development

  - Ongoing

- Performance Measures

  - Number of permits filed

  - Retention

  - Job creation

  - Program availability and engagement

  - Media coverage

  - Sector diversity

  - Main street report

- Regional Housing Study

  - 12-18 mo

- Agribusiness/Ag tourism

  - 24-36 mo

- Complete Appomattox River Trail & intersection w Fall Line

  - ~5 years

  - Funding for western portion

- Engage All Localities in PART

  - Ongoing

- Performance Measures

  - Population, migration

  - Walkability scores

  - Trail counts

  - Tourism—lodging and meals tax

  - Blue star families QOL

  - Housing cost burden

- Info Sheet

  - 12mo

- Convening CTE Program Reps

  - Ongoing

- Performance

  - Employment

  - Retention

  - Credentials

  - Clients served

  - Internships

- Multimodal Plan

  - 24-36mo

1:45 – Final thoughts, wrap-up